## Sheet1
Defect ID | Module | Description | Type | Severity | Priority | Status | Created Date | Assign
1 | User Login | 1. Describe: | User Interface | Medium | High | Closed | 2012-08-01 | HaoDN
When login successfully, screen login still maintain
2. Expected:
When login successfully, screen login will be displayed
2 | User Login | 1. Describe: | Miss requirement | Medium | High | Closed | 2012-08-01 | HaoDN
+ Login successfully
+ Only main screen is displayed
2. Expected:
The main screen and potential customer screen will be displayed
3 | User Login | 1. Describe: | Miss requirement | Medium | High | Closed | 2012-08-02 | HaoDN
+Login successfully
+Potential customer screen displayed all customers
2. Expected:
Potential customer screen will show only customer could buy product in 3 next days
4 | Main user | 1. Describe: | Miss requirement | Medium | High | Closed | 2012-08-01 | HaoDN
+ Open customer table
+ Delete one customer
+ No confirm message is displayed
2. Expected:
When delete on customer, confirm message will be displayed
5 | Main user | 1. Describe: | Miss requirement | Medium | High | Closed | 2012-08-01 | HaoDN
+ All buttons in main screen have no icon
2. Expected:
+ All button in main screen are intended of icons
6 | Backup data | 1. Describe: | Coding Logic | Cosmetic | High | Closed | 2012-08-02 | HaoDN
+Choose “Hệ Thống” in menu
+ Choose “Tạo bản sao dữ liệu”
+Naming and save
+ Failure
2. Expected:
+ Create backup successfully
7 | Backup data | 1. Describe: | Coding logic | Cosmetic | High | Closed | 2012-08-02 | HaoDN
+Choose “Hệ Thống” in menu
+ Choose “Phục hồi database”
+ Choose file backup
+ Click “Cancel”
+ Message successful, system turn off
2. Expected:
+ No restoring data
+ System normally operation
8 | User interface | 1. Describe: | User interface | Cosmetic | High | Closed | 2012-08-02 | HaoDN
+ Open insert or update customer
+ City is taken before District
2. Expected:
+ Address, district, city will displayed in turn
9 | Insert customer | 1. Describe: | Coding Logic | Cosmetic | High | Closed | 2012-08-02 | TuanNH
+ Open insert customer
+ Save
+ Taking map
+ Address is not loaded automatically.
2. Expected:
+ Address must be loaded automatically
10 | User interface | 1. Describe: | Coding Logic | Cosmetic | High | Closed | 2012-08-02 | TuanNH
+ Open insert customer
+ Save
+ Taking map
+ After search, address is changed
2. Expected:
+ After search, address must not be changed.
11 | Insert customer | 1. Describe: | Business logic | Medium | High | Closed | 2012-08-02 | HaoDN
+ Open insert customer
+ Enter “abc” in “Điện thoại” text
+Save successully
2. Expected:
+ “Điện thoại” text must not be entered character not number
12 | Insert customer | 1. Describe: | Business logic | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open insert customer
+ Enter less than 10 character in “Điện thoại” text
+Save successully
2. Expected:
+ “Điện thoại” text must not be entered less than 10 character number
13 | Insert customer | 1. Describe: | Business logic | Medium | High | Closed | 2012-08-03 | HaoDN
+Open customer table
+ Search by date
+ Enter start date after end date
+ Normally operation
2. Expected:
Start date must before end date
14 | Main user | 1. Describe: | Miss requirement | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open transaction table
+ Delete one transaction
+ No confirm message is displayed
2. Expected:
When delete on transaction, confirm message will be displayed
15 | Insert customer | 1. Describe: | Business logic | Medium | High | Closed | 2012-08-03 | HaoDN
+Open transaction table
+ Search by date
+ Enter start date after end date
+ Normally operation
2. Expected:
Start date must before end date
16 | Main form | 1. Describe: | User interface | Medium | High | Closed | 2012-08-03 | HaoDN
+Open main menu
+ “Danh sách khách hàng” “Danh sách hang hóa” is belong on “Hệ Thống”
2. Expected:
+ “Danh sách khách hàng” “Danh sách hàng hóa” must belong “Quản lý”
17 | Main form | 1. Describe: | User interface | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open main menu
+ “Khách hàng tiềm năng” is belong on “Báo cáo”
2. Expected:
+ “Khách hàng tiềm năng” is not belong on “Báo cáo”
18 | Main form | 1. Describe: | User interface | Medium | High | Closed | 2012-08-03 | HaoDN
+Login successfully
+ Potential customer screen is not center of screen
2. Expected:
+ Potential customer screen must be in center of the creen
19 | User interface | 1. Describe: | User interface | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open “Sổ khách hàng”
+ Icon add, update, delete have not tool tip
2. Expected:
+ All icon must have tool tip
20 | User interface | 1. Describe: | User interface | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open “Sổ bán”
+ Icon add, update, delete have not tool tip
2. Expected:
+ All icon must have tool tip
21 | Update customer | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open update customer screen
+ Change some information
+ Click icon “Đóng”
+ No message is displayed
2. Expected:
+ When change something in update screen, if click “Đóng”, message will be displayed
22 | Update transaction | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-03 | HaoDN
+ Open update transaction screen
+ Change some information
+ Click icon “Đóng”
+ No message is displayed
2. Expected”
+ When change something in update screen, if click “Đóng”, message will be displayed
23 | Main screen | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-04 | HaoDN
+Update some customer, transaction
+ No log is displayed in left menu
2. Expected:
+ All action in one session about customer and transaction will be log in left menu
24 | Update, insert customer | 1. Describe: | Miss requirement | Cosmetic | High | Closed | 2012-08-04 | HaoDN
+ Open update or insert customer
+No button create transaction
2. Expected:
+ In update or insert customer, there is a button to create transaction
25 | User interface | 1. Describe: | Coding logic | Cosmetic | High | Closed | 2012-08-04 | HaoDN
+ A call come in and nobody answer
+ No notification is displayed
2. Expected:
+ Notification will be displayed when there is any miscall
26 | Calling management | 1. Describe: | Coding logic | Cosmetic | High | Closed | 2012-08-04 | VuongND
+ Open two screen of system
+ A call come in
+ No pop up is displayed
2. Expected:
+ Any time, when a call come in, pop up will be displayed.
27 | Calling management | 1. Describe: | Miss requirement | Cosmetic | High | Closed | 2012-08-04 | VuongND
+ Open Calling screen
+ Screen is wrong displayed
2. Expected:
+ Screen calling will must be correctly with design
28 | Calling management | 1. Describe: | Miss requirement | Cosmetic | High | Closed | 2012-08-04 | VuongND
+Open Sending message screen
+ Cant send message to a lot of customer at same time
2. Expected:
+ Message could be sent to a lot of customer at same time
29 | Main screen | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoDN
+ Open “Hệ thống” in the main menu
+ There is “Cài đặt modem”
2. Expected:
In the “Hệ thống” menu, there is “Kiểm tra modem”
30 | Main screen | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoDN
+ Open “Hệ thống” in the main menu
+ Open “Cài đặt mẫu hóa đơn”
+ Can change in sample bill
2. Expected:
Cant change in sample bill
31 | Main screen | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-04 | HaoDN
+ Open “Quản lý” in menu
+ Choose “Danh sách hàng hóa”
+ Press “Thêm”
+No action
2. Expected:
+ Form add new product will be displayed
32 | Product manage | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoND
+ Open “Danh sách hàng hóa”
+Open Product table
+ All button delete, update, and save are not icon
2. Expected:
All button will be instead of icon
33 | Product manage | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoND
+ Open “Danh sách hàng hóa”
+Open “Danh sách bình vỏ”
+ All button delete, update, and save are not icon
2. Expected:
All button will be instead of icon
34 | Product management | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ All button delete, update, and save are not icon
2. Expected:
All button will be instead of icon
35 | Product management | 1. Describe: | User interface | Medium | High | Closed | 2012-08-04 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhà cung cấp”
+Open Product table
+ All button delete, update, and save are not icon
2. Expected:
All button will be instead of icon
36 | Account management | 1. Describe: | User interface | Medium | High | Closed | 2012-08-05 | HaoND
+ Open “Quản lý” in menu
+Open “Danh sách hàng hóa”
Open product table, click “Thêm” button
+ Title of screen add is wrong
2. Expected:
All title must be correct with design
37 | Account management | 1. Describe: | User interface | Medium | High | Closed | 2012-08-05 | HaoND
+ Open “Quản lý” in menu
+Open “Danh sách hàng hóa”
Open “Danh sách bình vỏ” and “Thêm” button
+ Title of screen add is wrong
2. Expected:
All title must be correct with design
38 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Quản lý ” tab
+ Click “Thêm button”
+Nhập “aaa” into “Điện thoại” text
+Click “Lưu”, no error
2. Expected:
“Điện thoại” text must not be entered character not number
39 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Nhân viên” tab
+ Click “Thêm button”
+Nhập “aaa” into “Điện thoại” text
+Click “Lưu”, no error
2. Expected:
“Điện thoại” text must not be entered character not number
40 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Quản lý ” tab
+ Click “Thêm button”
+Nhập less than 10 number into “Điện thoại” text
+Click “Lưu”, no error
2. Expected:
“Điện thoại” text must not be entered less than 10 number
41 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Người dùng” tab
+ Click “Thêm button”
+Nhập less than 10 number into “Điện thoại” text
+Click “Lưu”, no error
2. Expected:
“Điện thoại” text must not be entered less than 10 number
42 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Quản lý ” tab
+ Click “Thêm button”
+Nhập less 9 number or “aaa” into “Số CMT” text
+Click “Lưu”, no error
2. Expected:
“Số CMT” text must not be entered less than 9 number or entered character not number
43 | Staff management | 1. Describe: | Coding logic | Medium | High | Closed | 2012-08-05 | HaoND
+Open “Quản lý” in menu
+ Open “Danh sách nhân viên”
+ Choose “Người dùng” tab
+ Click “Thêm button”
+Nhập less 9 number or “aaa” into “Số CMT” text
+Click “Lưu”, no error
2. Expected:
“Số CMT” text must not be entered less than 9 number or enter character not number